## Sheet1
Module | Start Date | Completion Date | Resource | Description
AI Agent | 2022-11-07 | 2022-12-11 | Michael | Apart of initial MVP to setup the architecture, components will be highly coupled to get initial framework
Game Environment | 2022-11-07 | 2022-12-11 | Michael | Apart of initial MVP to setup the architecture, components will be highly coupled to get initial framework
Game Loop | 2022-11-07 | 2022-12-11 | Michael | Apart of initial MVP to setup the architecture, components will be highly coupled to get initial framework
Transmutter | 2022-12-12 | 2022-12-31 | Hargun | Core game mechanic
Player | 2022-12-12 | 2022-12-31 | Jonah | Core game mechanic
Actions | 2023-01-01 | 2023-01-22 | Jonah | Decoupling to add extensibility to actions
Monument | 2023-01-01 | 2023-01-22 | Hargun | Core game mechanic
Energy | 2023-01-01 | 2023-01-22 | Jonah | Decoupling to add extensibility to additional game mechanics (core mechanic)
JSON | 2023-01-01 | 2023-01-15 | Jeffrey | Needed to bridge simulation to data visualizer
Data Input | 2023-01-01 | 2023-01-15 | Jeffrey | Needed to bridge simulation to data visualizer
Pie Chart | 2023-01-01 | 2023-01-29 | Tianzheng | Visualize data to solve business goals, can be done in parrallel with other modules
Bar Graph | 2023-01-01 | 2023-01-29 | Tianzheng | Visualize data to solve business goals, can be done in parrallel with other modules
Line Graph | 2023-01-01 | 2023-01-29 | Tianzheng | Visualize data to solve business goals, can be done in parrallel with other modules